## Calculs
Task | Start on week | Task duration in weeks | Possible errors
Theory | 0 | 4 | 1
Design | 2 | 2 | 1
Dynamics | 3 | 2 | 1
Midterm presentation | 4 | 2 | 0
Control design | 5 | 2 | 1
Programming | 6 | 5 | 2
Simulation | 9 | 2 | 1
Report | 10 | 4 | 0
Final presentation | 12 | 2 | 0
Task | Start on week | Task duration in weeks | Possible errors
Theory | 0 | 3 | 0
Design | 2 | 5 | 0
Order componants | 4 | 3 | 0
Building and assembly | 5 | 3 | 0
Midterm presentation | 7 | 1 | 0
Simulation | 7 | 5 | 0
Dynamics | 9 | 4 | 0
Control | 10 | 3 | 0
Break | 13 | 2 | 0
Report | 14 | 1 | 0
Final presentation | 14 | 1 | 0